| Revision | Revision Description History | Date Released | Released By |
| --- | --- | --- | --- |
| 0 | Initial Release |  |  |

| Signature | Prepared by: | Reviewed by: | Approved by: |
| --- | --- | --- | --- |
| Name | Yoon Pauline | Ooi Chok Yan |  |
| Job Title | Manager | Chief Executive Officer |  |
| Date |  |  |  |

- Objective

  - The objective of this SOP is to establish the universal understanding of procedures, guidelines and goal of hosting or organizing Familiarization Trip.

- Scope

  - This SOP applies to all staffs under the Tourism Promotions Department and all personnel in PGT office responsible to conduct Familiarization Trip.

- Policy

  - To deliver comprehensive tourism products and update support toward maximizing understanding and increase the interest of Familiarization Trip participants to promote Penang as a tourism destination.

  - To collect and support to increase the data pool of overseas travel agencies and media for potential future collaboration.

  - To observe uniform strategies and execution methods and processes for all Familiarization activities.

  - To optimize the usage of allocated budget for Familiarization Trip and maximize the impact and return of each Familiarization hosted or organized.

- Procedures

Planning Stage

- Parties to confirm the event date, profile of group and the relevant information

- Agree on motif of visit

- Prepare itinerary for event

- Finalise itinerary

- Forward itinerary to external party on the itinerary for feedback

- Do the necessary changes on itinerary

- Obtain confirmation from external parties

Memo

- Prepare Memo (<RM10,000 approval from PGT CEO and > RM10,000 approval from the State Tourism EXCO)

- Approval obtained

- Seek Sponsorship Stage

Hotels

- Identify hotel & write to them

- Confirmation from hotel

Others

- Identify restaurants, places to visit etc

- Discuss with these parties if they are agreeable to sponsorship

- Receive confirmation from these parties

Transportation

- Obtain quotation

NOTE: Not only to select vendor in terms of cost, but based on expertise, work quality, type of vehicles, experience, services and overall suitability for the required project.

- Confirmation of transportation

Finance

- Prepare Purchase Requisition (PR) Form for all payment

- Submit PR for approval

- Send Purchase Order (PO) to vendors/suppliers

- Request Invoices

- Follow up payment with PGT Finance

Follow up

- News clipping/Campaign results

- End –