## PROJECT
PENANG GLOBAL TOURISM SDN BHD
YEAR ENDED DECEMBER 31, 2020
PROJECT STATUS AND EXPENSES RECOGNITION
[9 empty] | REVERSE FROM | DEFERRED | ADVANCED
| PROJECT SUPPLIER | PROJECT PARTICULARS | CAMPAIGN PERIOD | PROJECT TOTAL | AMOUNT PAID | AMOUNT PAID | INVOICED ON | STATUS/WORK DONE | EXPENSES | EXPENSES | BILLING | PREPAYMENT | EXPENSES |  | ACCOUNT
[5 empty] | IN 2020 | AFTER 2020
1 | AIR ASIA CO TRAVEL SDN BHD | PENANG FOOD CAMPAIGN WITH AIR ASIA SINGAPORE | DEC 20, 2020 - FEB 28, 2021 | 108000 |  | 32400 | 2020-12-30 | STARTED BUT POSTPONED DUE TO MCO | 75600 |  | 32400 |  |  | DR ADVANCE BILLING RM32,400
CR EXPENSES RM32,400
2 | SHOPBACK CASHBACK SDN BHD | TACTICAL CAMPAIGN WITH BOOKING.COM & SHOPBACK (RECOVERY) | NOV 2020 - JAN 2021 (INITIAL) | 600000 |  | 120000 | 2021-01-06 | STARTED BUT POSTPONED DUE TO MCO | 600000 |  |  |  |  | DR ACCRUAL RM600,000
|  |  | JAN 6, 2021 - APR 05, 2021 (POSTPONED) | [10 empty] | CR EXPENSES RM600,000
3 | FLYDAY | HK SOCIAL MEDIA CAMPAIGN-PRODUCTION AND SOCIAL MEDIA BOOSTING | WHOLE: DEC 2020 - FEB 2021 | 53000 |  |  |  | 2/3 AS AT YEAR END |  |  |  |  | 53000
|  |  | SUBSEC: DEC 2020 - JAN 2021 |  |  |  |  | 1/3 IN JAN 2021
4 | MALAYSIA CHINESE TOURISM ASSOCIATION (PG CHAPTER) | RECOVERY CAMPAIGN - SUBSIDY FOR TRAVEL PACKAGES (EXTENSION) | JULY 15, 2020 - OCT 15, 2020 (INITIAL) | 99790 |  | 1600 |  | BASED ON CLAIMS, LAST CLAIM IN DEC 2020 FOR RM1,600. | 98190 |  |  |  | 1600 | DR ACCRUAL RM98,190
|  |  | EXTENSION UNTIL MARCH 31, 2021 | [10 empty] | CR EXPENSES RM98,190
5 | KLOOK TECHNOLOGY SDN BHD | KLOOK & PG RECOVERY CAMPAIGN (BALANCE) | OCT 15, 2020 - FEB 15, 2021 | 600000 | 120000 |  | 2021-02-08 | PAID ACCORDING TO TERMS, AS AT DEC 2020, CONFIRMED WITH PROJECT MANAGER THAT THERE IS 20% WORK DONE | 480000 |  |  | 120000 |  | DR ACCRUAL RM480,000
CR EXPENSES RM480,000
6 | AIR ASIA | TOURISM RECOVERY TACTICAL CAMPAIGN WITH AIRASIA (BALANCE) | SEPT 28, 2020 - NOV 1, 2020 (INITIAL) | 500000 | 175000 |  | 2020-09-30 | CAMPAIGN 1 & 2 COMPLETE, CAMPAIGN 3 POSTPONED, TO PROVIDE 35% OF COST TO RECOGNISE AS EXPENSE | 150000 |  |  |  | 350000 | DR ACCRUAL RM150,000
|  |  | POSTPONED UNTIL AFTER INTERSTATE TRAVEL IS ALLOWED | [10 empty] | CR EXPENSES RM150,000
7 | FIREFLY | FIREFLY PG HUB MEDIA CAMPAIGN FOR NEW ROUTE |  | 100000 |  |  |  | NOT YET STARTED. 2021 PROJECT | 100000 |  |  |  |  | DR ACCRUAL RM100,000
CR EXPENSES RM100,000
8 | MATTA PENANG | TM FRANKFURT B2C ADVENT CALENDAR 2020 | EVENT ALREADY FINISH AND WINNERS TO COLLECT THEIR PRIZE | 6000 |  |  |  | ALREADY GOT WINNER BUT NOT YET CLAIMED, RECOGNIZE ONLY WHEN CLAIMED. DUE DATE END OF 2021 |  | 6000 |  |  |  | DR DEFERRED EXPENSES RM6,000
CR EXPENSES RM6,000
9 | EXPEDIA | DIGITAL MARKETING COLLABORATION WITH EXPEDIA & MAS | DEC 15, 2020 - APR 14, 2021 | 147000 |  |  | 2021-02-25 | ON GOING. TO PRORATE EXPENSES | 128625 |  |  |  | 18375 | DR ACCRUAL RM128,625.00
CR EXPENSES RM128,625.00
10 | D' SUNLIT SDN BHD | BILLBOARD ADS IN BRUNEI | DEC 31, 2020 - DEC 30, 2021 | 160829.24 |  |  | 2020-12-31 | NEXT YEAR EXPENSES |  |  | 160829.24 |  |  | DR ADVANCED BILLING RM160,829.24
CR EXPENSES RM160,829.24
11 | YTL INFO SCREEN SDN BHD | GIANT CUBE LED IN KL CITY CENTRE | FEB 1, 2021 - JUNE 30, 2021 (INITIALLY) | 53000 |  |  |  | 2021 PROJECT | 53000 |  |  |  |  | DR ACCRUAL RM53,000
|  |  | POSTPONED | [10 empty] | CR EXPENSES RM53,000
12 | PARISIGN MEDIA SDN BHD | EXTENSION OF COVERED WALKWAY ADS - KL CITY CENTRE | JUNE 01, 2021 - DEC 31, 2021 | 139570.2 |  |  |  | 2021 PROJECT | 139570.2 |  |  |  |  | DR ACCRUAL RM139,570.20
CR EXPENSES RM139,570.20
13 | CAN CAN PUBLIC ART PLT | EXTENSION OF PICAF | JUNE 01, 2020 - DEC 31, 2021 | 89700 |  | 30500 | 2021-01-05 | APPORTION ACCORDING TO TIME FRAME | 59200 |  |  |  | 30500 | DR ACCRUAL RM59,200
CR EXPENSES RM59,200
[9 empty] | 1884185.2 | 6000 | 193229.24 | 120000 | 453475
[9 empty] | DR | ACCRUALS |  | 1884185.2
[9 empty] | DR | DEFERRED EXPENSES |  | 6000
[9 empty] | DR | PREPAYMENT |  | 120000
[9 empty] | DR | ADVANCED BILLING |  | 193229.24
[10 empty] | CR EXPENSES |  |  | 2203414.44