## GC Original
2016 PDC FINANCIAL STATEMENT TIMELINE
| No |  | Tasks | Auditors | Remark | Status |  |  |  |  | No of days | Timeline | 2017-01-01 | [30 empty] | 2017-02-01 | [27 empty] | 2017-03-01
[6 empty] | Interim Audit | Preparation of Accounts | Accounts Review | Submission to Auditor | Audit |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| 1 | PDC | Bank Reconciliation | MNZWAJ Associates | [6 empty] | 3 | 2017-01-05 | 2017-01-01 1: New Year; 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 7: weekend; 2017-01-01 14: weekend; 2017-01-01 21: weekend; 2017-01-01 28: weekend; 2017-01-01 30: Chinese New Year; 2017-02-01 4: weekend; 2017-02-01 11: weekend; 2017-02-01 18: weekend; 2017-02-01 25: weekend; 2017-03-01 4: weekend; 2017-03-01 11: weekend; 2017-03-01 18: weekend; 2017-03-01 25: weekend
| 2 |  | December Budget Review | [7 empty] | 5 | 2017-01-09 | 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 6: 4; 2017-01-01 9: 5
| 3 |  | Reconciliation Interco Transaction | [7 empty] | 8 | 2017-01-12 | 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 6: 4; 2017-01-01 9: 5; 2017-01-01 10: 6; 2017-01-01 11: 7; 2017-01-01 12: 8
| 4 |  | Management Account For YE 2016 | [7 empty] | 14 | 2017-01-20 | 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 6: 4; 2017-01-01 9: 5; 2017-01-01 10: 6; 2017-01-01 11: 7; 2017-01-01 12: 8; 2017-01-01 13: 9; 2017-01-01 16: 10; 2017-01-01 17: 11; 2017-01-01 18: 12; 2017-01-01 19: 13; 2017-01-01 20: 14
| 5 |  | Discussion with CFO (Co level) - Draft | [7 empty] | 17 | 2017-01-25 | 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 6: 4; 2017-01-01 9: 5; 2017-01-01 10: 6; 2017-01-01 11: 7; 2017-01-01 12: 8; 2017-01-01 13: 9; 2017-01-01 16: 10; 2017-01-01 17: 11; 2017-01-01 18: 12; 2017-01-01 19: 13; 2017-01-01 20: 14; 2017-01-01 23: 15; 2017-01-01 24: 16; 2017-01-01 25: 17
| 6 |  | Final PDC Co. Level | [7 empty] | 20 | 2017-01-31 | 2017-01-01 3: 1; 2017-01-01 4: 2; 2017-01-01 5: 3; 2017-01-01 6: 4; 2017-01-01 9: 5; 2017-01-01 10: 6; 2017-01-01 11: 7; 2017-01-01 12: 8; 2017-01-01 13: 9; 2017-01-01 16: 10; 2017-01-01 17: 11; 2017-01-01 18: 12; 2017-01-01 19: 13; 2017-01-01 20: 14; 2017-01-01 23: 15; 2017-01-01 24: 16; 2017-01-01 25: 17; 2017-01-01 26: 18; 2017-01-01 27: 19; 2017-01-01 31: 20
| 7 |  | Interim Audit |  |  | 2017-02-06 |  |  |  |  | 15 | 2017-02-17 | 2017-02-01 6: 1; 2017-02-01 7: 2; 2017-02-01 8: 3; 2017-02-01 9: 4; 2017-02-01 10: 5; 2017-02-01 13: 6; 2017-02-01 14: 7; 2017-02-01 15: 8; 2017-02-01 16: 9; 2017-02-01 17: 10
| 8 |  | Working PDC Group Conso Account |  |  |  |  | 2017-02-01 |  |  | 14 | 2017-02-13 | bar: 2017-02-01 6 to 2017-02-01 10; 2017-02-01 13 to 2017-02-01 17
| 9 |  | Draft PDC Group Conso Account |  |  |  |  | 2017-02-14 |  |  | 2 | 2016-02-17 | 2017-02-01 1: 1; 2017-02-01 2: 2; 2017-02-01 3: 3; 2017-02-01 6: 4; 2017-02-01 7: 5; 2017-02-01 8: 6
| 10 |  | Final Group Consolidated Account |  |  |  |  | 2017-02-20 |  |  | 12 | 2017-02-24 | 2017-02-01 9: 1; 2017-02-01 10: 2; 2017-02-01 13: 3; 2017-02-01 14: 4; 2017-02-01 15: 5; 2017-02-01 16: 6; 2017-02-01 17: 7; 2017-02-01 20: 8; 2017-02-01 21: 9; 2017-02-01 22: 10; 2017-02-01 23: 11; 2017-02-01 24: 12
| 11 |  | Group Conso review by consultant |  |  |  |  | 2017-02-17 |  |  | 13 | 17/2/2017 - 28/2/17 | 2017-02-01 10: 1; 2017-02-01 13: 2; 2017-02-01 14: 3; 2017-02-01 15: 4; 2017-02-01 16: 5; 2017-02-01 17: 6; 2017-02-01 20: 7; 2017-02-01 21: 8; 2017-02-01 22: 9; 2017-02-01 23: 10; 2017-02-01 24: 11; 2017-02-01 27: 12; 2017-02-01 28: 13
| 12 |  | Draft Group Financial Statement 2016 | [8 empty] | 2017-03-03
| 13 |  | Table Group A/c to KPITF |  | During Mac 2017 | [6 empty] | 2017-03-07
| 14 |  | Table Group A/c to ARC | [8 empty] | 2017-03-14
| 15 |  | Table Group A/c to Board | [8 empty] | 2017-03-17
| 16 |  | Submit to JAN | [8 empty] | 2017-03-22
#REF! | 17 | Subsidiaries | Pedeco | AljefrriDean |  | 2016-11-10 | 2-3/1/17 | 2017-01-04 | 2017-01-04 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 18 |  | Info Melia Sdn Bhd | AljefrriDean |  | 2016-11-01 | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 19 |  | PDC Homes | AljefrriDean |  | 2016-11-21 | 2-4/1/17 | 2017-01-04 | 2017-01-04 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 20 |  | PDC Event | AljefrriDean |  | 2016-11-10 | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 21 |  | PDC Horizon Sdn Bhd | AljefrriDean |  | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 22 |  | PDC Horizon Management Sdn Bhd | AljefrriDean |  | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 23 |  | Premier Horizon Ventures Sdn Bhd | AljefrriDean |  | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 24 |  | BPO Premier Sdn Bhd | AljefrriDean |  | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
#REF! | 25 |  | Penang Int Technology Park SB | AljefrriDean |  | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
| 26 |  | Majestic Showcase S/B (DOI 18/5/16) | AljefrriDean | Period < 1 year | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
| 27 |  | Pristine Junction S/B (DOI 28/4/16) | AljefrriDean | Period < 1 year | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
| 28 |  | Stunning Structures S/B (DOI 20/4/16) | AljefrriDean | Period < 1 year | n/a | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
1 | 29 |  | PDC Consultancy | AljefrriDean |  | 2016-11-09 | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
2 | 30 |  | PHC Management | AljefrriDean |  | 2016-11-10 | 2-3/1/17 | 2017-01-04 | 2017-01-05 | 2017-01-09 | 17 | 2017-02-01 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17
3 | 31 |  | PDC Premier | AljefrriDean |  | 2016-11-14 | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | Co.11 Grp.8 | Co. 7/2/2017 Group 15/2/2017 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
4 | 32 |  | PDC Properties | AljefrriDean |  | 2016-11-21 | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-09 | 16 | 2017-02-07 | 2017-01-01 9: 1; 2017-01-01 10: 2; 2017-01-01 11: 3; 2017-01-01 12: 4; 2017-01-01 13: 5; 2017-01-01 16: 6; 2017-01-01 17: 7; 2017-01-01 18: 8; 2017-01-01 19: 9; 2017-01-01 20: 10; 2017-01-01 23: 11; 2017-01-01 24: 12; 2017-01-01 25: 13; 2017-01-01 26: 14; 2017-01-01 27: 15; 2017-01-01 31: 16; 2017-02-01 1: 17; 2017-02-01 2: 18; 2017-02-01 3: 19; 2017-02-01 6: 20; 2017-02-01 7: 21
5 | 33 |  | PDC Telco | Wong Liu |  | n/a | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | 11 | 2017-01-31 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11
6 | 34 |  | PDC Setia Urus | AljefrriDean |  | 2016-12-01 | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
7 | 35 |  | PDC Nusabina | AljefrriDean |  | 2016-12-14 | 2-9/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
8 | 36 |  | Pintar Daya sdn Bhd | JL Ong |  | n/a | 2-3/1/17 | 10-11/1/17 | 2017-01-12 | 2017-01-16 | 11 | 2017-01-31
9 | 37 |  | PIHH Development | AljefrriDean |  | n/a | 3-10/1/17 | 11-12/1/17 | 2017-01-13 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
10 | 38 |  | PH Geletine Sdn Bhd | AljefrriDean |  | n/a | 3-10/1/17 | 11-12/1/17 | 2017-01-13 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
11 | 39 |  | IGP | Moores Rowland |  | n/a | 3-6/1/2017 | 2017-01-09 | 2017-01-10 | 2017-01-16 | 11 | 2017-01-31 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14
12 | 40 |  | PICEB Sdn Bhd | AljefrriDean |  | 13-14/12/2016 | 2-9/1/17 | 2017-01-09 | 2017-01-10 | 2017-01-16 | 11 | 2017-01-31 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14
13 | 41 |  | Penang Global Tourism | AljefrriDean |  | 29/11 - 1/12/16 | 3-10/1/17 | 11-12/1/17 | 2017-01-13 | 2017-01-16 | 16 | 2017-02-07 | 2017-01-01 16: 1; 2017-01-01 17: 2; 2017-01-01 18: 3; 2017-01-01 19: 4; 2017-01-01 20: 5; 2017-01-01 23: 6; 2017-01-01 24: 7; 2017-01-01 25: 8; 2017-01-01 26: 9; 2017-01-01 27: 10; 2017-01-01 31: 11; 2017-02-01 1: 12; 2017-02-01 2: 13; 2017-02-01 3: 14; 2017-02-01 6: 15; 2017-02-01 7: 16
14 | 42 | Associates | PDC Heritage Hotel Sdn Bhd | HLB Ler Lum |  | n/a | [5 empty] | 23/1/2017
15 | 43 |  | Business & Budget Hotel (Png) SB | HLB Ler Lum |  | n/a | [5 empty] | 23/1/2017
16 | 44 |  | Business & Budget Hotel (S'Jaya) SB | HLB Ler Lum |  | n/a | [5 empty] | 23/1/2017
17 | 45 |  | Tropical Island Resort Sdn Bhd | Azmzn, Wong Salleh & Co | Disposal of Associates | n/a | [5 empty] | 23/1/2017
18 | 46 |  | Bayan Baru Specialist Hospital SB | PWC |  | n/a | [5 empty] | 23/1/2017
19 | 47 |  | Dynaview Sdn Bhd | Messrs BDO |  | n/a | [5 empty] | 23/1/2017
20 | 48 |  | E&O-PDC Holdings Sdn Bhd | E&Y |  | n/a | [5 empty] | 23/1/2017
21 | 49 |  | KDPP Holdings Sdn Bhd | Ram J & Co |  | n/a | [5 empty] | 23/1/2017
22 | 50 |  | Penang Commercial & Ind Dev Bhd | Khoo Khai Hong |  | n/a | [5 empty] | 23/1/2017
23 | 51 |  | Georgetown Bids Sdn Bhd | BOD |  | n/a | [5 empty] | 23/1/2017
Work done
WIP
submission management a/c to auditor
1st darft audited report
final draft audited report
|  | Notes | [8 empty] | Status
As at 6 January 2015
|  | 1) | Final Audit by EY start 26 Jan 2015
|  | 2) | Final audit PGT by EY start 26 Jan 2015
|  | 3) | Deadline for Associates Companies 26 Jan 2015
|  | 4) | PIHH & PH Gelatin need to consolidate

## Sheet1
Premier Subsidiaries (100%)
| Company Name | Auditor
1 | Pedeco | AljefrriDean
2 | Info Melia Sdn Bhd | AljefrriDean
3 | PDC Homes | AljefrriDean
4 | PDC Event | AljefrriDean
5 | PDC Consultancy | AljefrriDean
6 | PHC Management | AljefrriDean
7 | PDC Premier | AljefrriDean
8 | PDC Properties | AljefrriDean
9 | PDC Setia Urus | AljefrriDean
10 | PDC Nusabina | AljefrriDean
11 | PDC Telco | Wong Liu
1 | Pintar Daya sdn Bhd | JL Ong
PDC Subsidiaries (100%)
1 | IGP | Moores Rowland
2 | Penang Global Tourism | EY
3 | PIHH Development | AljefrriDean
4 | PH Geletine Sdn Bhd | AljefrriDean
5 | PDC Horizon Management | AljefrriDean
6 | PDC Horizon Venture | AljefrriDean
7 | PDC Horizon | AljefrriDean
8 | BPO Premier | AljefrriDean
9 | PITP | AljefrriDean
Associates
11 | PDC Heritage Hotel Sdn Bhd | HLB Ler Lum
12 | Business & Budget Hotel (Png) SB | HLB Ler Lum
13 | Business & Budget Hotel (S'Jaya) SB | HLB Ler Lum
14 | Tropical Island Resort Sdn Bhd | Azmzn , Wong Salleh & Co
15 | Bayan Baru Specialist Hospital Sdn Bhd | Pricewaterhouse Coopers
16 | Dynaview Sdn Bhd | Messrs BDO
17 | E&O-PDC Holdings Sdn Bhd | E&Y
18 | KDPP Holdings Sdn Bhd | Ram J & Co
19 | Penang Commercial & Industrial Development Bhd | Khoo Khai Hong
20 | Georgetown Bids Sdn Bhd

## by table (hidden)
| Account |  | Audit
Details | 1st Draft | 2nd draft | Audit Start | 1st darft | 2nd draft
|  | 1 week after | 1 week after
Segment | 2015-01-09 | 2015-01-16
Company | 2015-01-13 | 2015-01-20 | 2015-01-22 | 2015-02-12 | 2015-02-18
Consolidation Premier | 2015-01-19 | 2015-01-26
Consolidation PDC Grp | 2015-01-23 | 2015-01-30