## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 11 | Commissions Received |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle/Janice
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify the commissions received by PGT | 2014-09-18 | 2014-09-13 | Selling of GTF ticket in year 2012 | No | N/A | No | N/A
2 | Review current contracts on the availability of GST clauses (especially for contracts that will span until GST implementation date). | 2014-09-18 | 2014-09-13 | No contract/agreement was signed between GTF and PGT. No ticket selling in PGT for year 2013-2014 | No | N/A | No | N/A
3 | Evaluate whether current contracts will be required to be revised if it span through GST implementation date. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
4 | Establish process to include GST clause in all new service agreement (where necessary). | 2014-09-18 | 2014-12-01 | Will establish a new process to include GST if PGT provide services on behalf vendor | No | To prepare a process for commision receive in next future | No | N/A
5 | Determine whether PGT will issue tax invoice or the vendor will issue a self-billed invoice to PGT. | 2014-09-18 | 2014-09-13 | Vendor should issue a tax invoice to PGT for commission received | Yes | To follow with vendor if PGT continue to provide the service | No | N/A
6 | Establish process and procedures to account GST on the commissions received in the current taxable period (earlier of payment received or tax invoice issued). | 2014-09-18 | 2014-09-13 | Will establish a new process on time of supply to account for GST if PGT continuously provide services on behalf vendor | Yes | To prepare a process for time of supply in next future | No | N/A
7 | Communicate the GST implications to the vendors and agree on which party to bear the GST cost. | 2014-09-18 | 2014-09-13 | To communicate with vendor in next future | No | N/A | No | N/A
8 | Implement the required changes on the process and procedures. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
9 | Educate employee on the changes. | 2014-09-18 | 2014-09-13 | To communicate with staff about GST impact on commission received | No | N/A | No | N/A