## GST-12
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 12 | Sundry Income & Misc Expenditure |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify the type of income and expenses that are posted into sundry receipt and general expense account | 2014-09-11 | 2014-09-09 | As per list attached | Yes | Two type of suppliers - GST register and non GST register | Yes | To mannually keep track suppliers for GST or non GST, and input tax or no input tax incurred. Some of the suppliers are unique as they might be the only supplier for certain goods | Not yet started
2 | Ascertain the GST treatment on each type of income and expense identified | 2014-09-11 | 2014-09-09 | As per list attached | Yes | To imposed 6% of GST for all sales (taxable supply) | Yes | POS System in TIC will be upgraded | POS system to be upgraded in Feb 2015 (According to vendor)
3 | Identify the process and system change required to account for GST appropriately | 2014-09-11 | 2014-09-09 | Currently sales & purchases with no gst impact | Yes | To account 6% input tax and impose 6% output tax for all taxable supply | Yes | POS System in TIC will be upgraded | POS system to be upgraded in Feb 2015 (According to vendor)
4 | Implement the process and system changes | 2014-09-11 | TBA | Currently POS system without GST compliance | Yes | To upgrade POS system | Yes | POS System in TIC will be upgraded | "
5 | Communicate the updated process and system changes to the relevant employees | 2014-09-11 |  | To discuss with head of department | No | N/A | No | N/A

## GST-12 List of Sundry
Penang Global Tourism Sdn Bhd
Sundy Income/Other Income | Tax Coding | GST Impact
|  | Standard Rated | Zero Rated | Exempted | Out-of-Scope
Sales - Souvenirs | SR | x
Sales - Tours (by travel agent/PGT engage a tour guide) | SR | x
Sales - Rapid Passport | SR | x
Sales - Korea Exhibition Art | SR | x
Sales - Stamps | SR | x
Misc Expenditure
Stamp duty and Administrative charge for contract | TX | x
Penalty under estimate Tax | OP |  |  |  | x

## GST-12 Flow Chart
Invoice from Suppliers (consignment goods / purchases)
Payment proess
Matching invoices with merchandise sales record/Official receipts
Invoice verified, checked and signed by Department Head
Return to Supplier/Vendor
YES
NO