## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 19 | Employee Benefits |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle & Hooi Leng
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and determine the category of goods or services that are provided to employees. | 2014-09-11 | 2014-09-11 | Nil | No
2 | Identify items covered under your employee benefits and its respective GST treatment | 2014-09-11 | 2014-09-11 | Refer to Appendix I | Yes | Management is to decide and come out with a new P&P | No | N/A
3 | Identify items that are subjected to deemed output tax | 2014-09-11 |  | Uniform to driver No free goods to employees | No | N/A | Yes | To create a GL code - employee benefits (DS)
4 | Seek clarification from Customs on any ambiguity in GST treatment | 2014-09-11 |  | Nil
5 | Update HR policy, guidelines, processes and systems changes for GST compliance on free goods to employees | 2014-09-11 | 2014-09-11 | Nill. No free goods to employees | No | N/A | No | N/A
6 | Develop a process to ensure that deemed output tax is correctly accounted in PGT’s GST returns based on time of supply | 2014-09-11 | 2014-09-11 | Based on Actual Tax Point - Tax Invoice receive | Yes | A process to account for output tax based on time of supply is prepared | Yes | To generate invoice and account output tax
7 | Educate staff on the updated policy, processes and systems changes | 2014-09-11 | 2015-01-31 | To communicate with staff once new policy is done

## Appendix I
Appendix I
Employee Benefits |  | Type | GST Tax Code
i | Medical
| - Medical Claim | Claims | BL
ii | Insurance
| - Group Hospital & Surgical | non-cash | BL
| - Group Term Life | non-cash | BL
iii | Allowance
| - Guaranteed Minimum Overtime Allowance | Cash | OP
| - Handphone Allowance | Cash | OP
| - Outstation Meal Allowance | Cash | OP
| - Airport Meal Allowance | Cash | OP
iv | Claim
| - Overtime | Cash | OP
| - Mileage | Cash | OP
| - Parking & Toll | Claims | TX
| - Handphone (as per bill) | Claims | OP
v | Airport Car Park | Claims | TX
vi | Rapid Bus Monthly Pass | Claims | OP
vii | Uniform | Claims | DS
viii | Gratuity | Cash | OP
ix | Training & Development
| - Workshop/Course | non-cash | TX
| - Teambuilding | non-cash | TX
x | Company Car | non-cash | OP
xi | Annual Dinner | non-cash | TX

## Deemed Supplied Process
Deemed Supplies - Time of Supply
Actual Tax Point
Goods purchase
(tax invoice/simplified tax invoice)
Account for GST Output tax
Input Tax Credit