## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 20 | Reimbursement of Staff Expenses / Claims |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify all types of reimbursement claims made by staff of PGT. | 2014-09-11 | 2014-09-11 | Refer listing | No | N/A | No | N/A
2 | Categorise reimbursement claims as business expenses or private expenses. | 2014-09-11 | 2014-09-11 | Yes. All reimbursement claims are business expense | No | N/A | No | N/A
3 | Review and establish systems and processes to deal with reimbursement claims to ensure that input tax claims are maximised and that blocked input tax is not claimed | 2014-09-11 |  | Claims form/Statement of claims is use for reimburesment | Yes | To analyse each of every claims whether fall under input tax claim or block input tax | No | N/A
4 | Establish a standard policy on employees reimbursement (e.g. fringe benefits, business expenses, etc.) taking into the consideration the following requirements:
| Valid tax invoice to be provided by employee (tax invoice must be in the name of the relevant entity claiming the input tax) | 2014-09-11 |  | All tax invocie /simplified tax invoice has to be the name of PGTSB | Yes | To prepare a process work flow for reimbursement | No | N/A
| GST is genuine (i.e. issued by GST registered supplier) | 2014-09-11 |  | Suppliers must be register with GST | Yes | To update and checking the suppliers master listing from time to time | No | N/A
| Where no valid tax invoice provided (i.e. PGT cannot claim input tax), to consider whether PGT to absorb cost of GST not claimable, or, to disallow reimbursement of GST element to the employee. | 2014-09-11 |  | No valid tax invoice provided (Air fare, Hotel Accommodation, sundry income, food and refreshment) | Yes | Management to decide whether to absorb the 6% of GST not claimable or disallow reimbursement of GST by employees | No | N/A
8 | No input tax is claimed by PGT where it is disallowed. For example: - No valid tax invoice available - Expenses relate to blocked input tax items - Expenses where foreign GST/VAT is incurred (foreign GST/VAT cannot be claimed under Malaysian GST system) | 2014-09-11 |  | Input tax disallow : - foreign GST/VAT (Hotel/Transportation) - Block input tax (Entertainment for other person) | Yes | To check claim reimbursement based on ITC guideline | No | N/A
9 | Establish processes, documentation and system changes required to implement policy. | 2014-09-11 |  | A procedure of reimbursement ill be prepared | Yes | To prepare a procedure of reimbursement by staff | Yes | To capture transaction base on GST tax coding
10 | Ensure record keeping requirements are adequate for GST purposes | 2014-09-11 |  | All reimbursement must have supporting document (tax invoices, receipts) | Yes | To include in the procedure | No | N/A
11 | Update current processes and systems to reflect the GST treatment. | 2014-09-11 |  | Refer to flow chart | Yes | To check reimbursment base on GST guideline : - Valid Tax Invoice - Input tax Claimable - Blocked input tax | No | N/A
12 | Educate staff on processes and systems changes. | 2014-09-11 |  | To update and communicate to staff once the procedure ready

## GST20 - Reimbursement
GST 20– Reimbursement of staff expenses / claims
No. | (1) Reimbursement of expense Please provide a brief description |  | (2) General Ledger account code Please provide GL account code number | (3) Is reimbursement in respect of business expense? Please select from drop down menu | (4) Is reimbursement made to a non-employee? Please select from drop down menu | (5) GST tax code (expense) Please select from drop down menu | Drop-down menu data
[7 empty] | Column (3) | Column (4) | Column (5)
1 | Medical Fee | Medical Fee | 9006/000 | No | No | BI | Yes | Yes | FITC
2 | Medical Fee | Medical Fee | 9006/001 | No | No | BI | No | No | NITC
3 | Allowance | H/P Allowance, Food Allowance | 9002/000 | No | Yes |  |  |  | BI
4 | Mileage/Toll Claims/Petrol | Mileage/Toll Claims/Petrol | 9014/000 | Yes | No
|  | - Petrol Refill |  | Yes | No
|  | - Mileage Reimbursement |  | Yes | No
|  | - Parking Fees Reimbursement |  | Yes | No
5 | Tic-Mileage/Toll Claims/Petrol | Tic-Mileage/Toll Claims/Petrol | 9014/001 | Yes | No
|  | - Mileage Reimbursement |  | Yes | No
|  | - Parking Fees Reimbursement |  | Yes | No
|  | - Rapid Passport Monthly |  | Yes | No
6 | Local Travel | - Hotel Accommodation | 9015/000 | Yes | No
|  | - Air Fare (Domestic) | 9015/000 | Yes | No
|  | - Transportation (Eg Taxi, Mrt) | 9015/000 | Yes | No
|  | - Parking Fees | 9015/000 | Yes | No
|  | - Food And Beverages Reimbursement | 9015/000 | Yes | No
7 | Staff Uniform | Staff Uniform (Not Stated In Contract) | 9017/000 | No | No
8 | Telephone/Emails/Fax | - Telephone Charges | 9101/000 | Yes | No
|  | - H/P Rreimbursement From Staffs (Monthly Rm50/According To Billing) | 9101/000 | Yes | No
|  | - H/P Data Usage | 9101/000 | Yes | No
9 | Postage & Courier | Postage & Courier | 9102/000 | Yes | No
10 | Stationery & Supplies | Stationery & Supplies | 9105/000 | Yes | No
11 | Refreshment & Food | - Food & Refreshment For Staff | 9109/000 | No | Yes
|  | - Refreshment For Bod/Meeting | 9110/000 | Yes | No
12 | Upkeep of M/Vehicle | - Insurance/Road Tax | 9111/000 | Yes | No
13 | Familiazation Trip | - Tour Guide/Trishaw/Nature Tour | 9300/004 | Yes | Yes | BI
|  | - Entertainment For Travel Agent (Lunch, Dinner) | 9300/004 | Yes | Yes | BI
|  | - Souvenirs For Delegates | 9300/004 | Yes | No
14 | Hosting of events | - Social Media Ads | 9300/024 | Yes | No
|  | - Allowance For Rela Volunteers | 9300/024 | Yes | No
15 | Tourism Promotion | - Hotel Accommodation (overseas) | 9400/108 - 9400/118 | Yes | No
|  | - Transportation (Overseas) |  | Yes | No
|  | - Meal Allowance |  | Yes | No
|  | - Souvenirs |  | Yes | No
|  | - Internet Charges |  | Yes | No
|  | - Food & Refreshment |  | Yes | No
|  | - Wrapping Cost |  | Yes | No
|  | - Visa |  | Yes | No
No

## Work Flow
Finance Dept to review of claim and checking (receipts,billing)
Department head to counter check and verify
YES
Approved by CEO/MD/GM
NO
Reimbursement form fill in by employee
Return to employee
YES
Payment process
NO

## Work Flow (GST Impact)
Finance Dept to review of claim and checking
Department head to counter check and verify
YES
Approved by CEO/MD/GM
NO
Reimbursement form fill in by employee
Return to employee - To get a new tax invoice
- PGT to absorb the 6% or Employees are not allow to claim the 6% GST incurred
YES
Payment process
NO
GST Impact - To review
- Valid Tax Invoice (Bill to PGTSB) - Input Tax Claimable - Blocked input tax
NO