## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 21 | Goods Provided for Free |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC:
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Review and assess marketing strategies from different channels to determine whether any cash / cash rebate, free goods, free services, vouchers, or any other kind of incentives provided. | 2014-09-11 |  | Only free goods/souvenirs give out : Type of souvenirs/gifts: - Memo pad - Pen - Mugs - Pewter trishaw - Tiles Fridge Magnet - Cotton Bags - Paper bag - Collar Pin - Books - Tau Sar Pneah - ?? Food or souvenirs - Tourism Booklet - ??? - Tourism DVD - ??? | No | N/A | No | N/A
2 | Segregate and record free gifts given from own stock and those received from suppliers. | 2014-09-11 |  | Currently record inventory based on product basis only | Yes | To have addiditonal spreadsheet on company/association that request for free goods | Yes | To account for GST if the free gifts exceeded RM500 for each person/company
3 | Analyse feasibility to track GST gift rule (i.e. RM500 per person per year), taking into account amongst others the following: a. Type of goods given for free (e.g. free goods, free services, non-cash voucher, etc.) b. Value of goods given for free c. Frequency of goods given for free d. Ability to identify recipient of free goods (e.g. to employees, distributors, suppliers, etc.) | 2014-09-11 |  | To amend inventory record tracking | Yes | - To include value of the goods inventory record, identify recipient, frequency of free goods given (including, Free souvenirs for Road Show - Overseas, free goods to university/associations/company/person(fam trip/guests)/staffs | Yes | To account for GST (DS) if the free gifts exceeded RM500 for each person/company (Time of supply for free goods given during roadshow : - Date the goods given out during trade show, officer need to record the recipient everyday
4 | Awareness of deemed supplies and GST output tax when formulating marketing strategies in the future. | 2014-09-11 |  | Free goods given for free to support tourism industry players, promote penang during road show | Yes | To discuss with marketing department on the strategies | No | N/A
5 | Management to make strategic decision on whether goods will continue to be given free, the value of such gifts and whether PGT will attempt to track free goods. | 2014-09-11 |  | Free goods given for free to support tourism industry players, promote penang during road show | Yes | To discus with GM & head of department whether goods will be given free in future | No | N/A
6 | Consider alternative marketing structure / packages taking into account the GST implication. | 2014-09-11 |  | To discuss with GM and department head | Yes | To discuss with marketing department on the strategies | No | N/A
7 | Consider proper controls for goods given out for free – map process flow of goods given away free to ensure GST output tax is captured timely. | 2014-09-11 | 2014-12-01 | A process/procedure of free goods requsition and given out will be prepared | Yes | All requsition and free goods given will be followed the process/procedure | No | N/A | To be completed
8 | Determine changes required to existing policy, processes and system to ensure GST output tax is accounted for appropriately for the various incentives / gifts provided. | 2014-09-11 |  | Inventory record for free goods | Yes | To include value, recipient and date goods give out Person-in charge to monitor the goods given out whether is exceed RM500, to be notify Finance Department | No | N/A
9 | Implement changes. | 2014-09-11 | 2014-12-01 | Changes will be implemented once the procedure is done | No | N/A | No | N/A
10 | Educate and communicate policy to staff on policy on free goods. | 2014-09-11 | 2014-11-01 | To communicate with staffs on the policy | No | N/A | No | N/A