## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 22 | Free Services |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle/Jason/Darren
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify free services provided by PGT and segregate these by its intended recipient (i.e. employees, third party or 'connected persons'). | 2014-09-11 | 2014-09-11 | Free services provided by PGT : 1. Free Cemetery Tour (open to public) 2. Free Guided walk at Botanic Garden (open to public) 3. Free Performance (open to public/travel associate) Question : if we give free services to a company, in return they will put PGT logo in their brochure as suppoted by PGT. Is this consider free services or sponsorship? | No | N/A | No | N/A
2 | Assess the GST treatment and impact for each transaction. | 2014-09-11 | 2014-09-11 | Free tours & performances | Yes | There will be a standard rate charge on each transaction, but no input tax are allow for Tours (entertainment), tax coding will be BL Question : Free performances is consider as entertainment? | Yes | To capture the transaction based on tax coding BL/TX
3 | For each transaction which has a GST impact ensure that the valuation of the supply adheres to the open market value ("OMV"). | 2014-09-11 |  | Two type of senario: 1. Free services provided to public/travel associate (one way supply - no GST impact) 2. Free services provided to company/travel associate in returns with free goods and ads (refer to sponsorship) | Yes | To determine free services and discuss with management / head of deparment on free services strategies ("only services provided for no consideration") | No | N/A
4 | Update processes and systems to track these transactions (services provided for no consideration) and account for GST accordingly. | 2014-09-11 |  | A new process/procedures to be prepared | Yes | Record tracking to be include: - free services to third party with no returns (gst impact = allow to claim input tax) - free services(tours/performances) to third party with no returns (gst impact = input tax blocked) | No | N/A
5 | Educate staff on the updated processes and systems changes | 2014-09-11 |  | To communicate with staff once the process and procedure is ready