## Readiness report
GST Issues Log | [8 empty] | STATUS
[11 empty] | Not yet started | Not Yet Started
|  |  | 26 | Sponsorship | [5 empty] | In Progress | In Progress | In Progress
[11 empty] | Done | Done
PIC: All Staff
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | In - returns | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and categorise sponsorships that PGT has been involved. | 2014-09-18 | 2014-09-17 | Sponsorship given by PGT : a) Publicity (Printing of brochures, billboard, bus wrap) for events (not organize by PGT) b) Performance (Traditional, culture dance) for dinner/events c) Cash Sponsorship d) Dinner/tours/hotel for media & travel agent e) Promoting events in PGT website/Facebook Q : Some sponsorship may not pay directly to organizer, we pay directly to supplier/vendor engaged by PGT, Is this still consider as sponsorship or free services (GST impact)?? | a) by mention PGT and putting PGT logo in their media release b) putting logo in their brochures (supported by PGT) c) putting logo in their brochures (supported by PGT) d) Article/write-up about Penang in their magazine/blogs etc e) putting logo in their brochures (supported by PGT)
2 | Develop a policy on sponsorship/donation arrangement for PGT, taking into the account the following: Sponsorship/Donation received by PGT a) Identify nature of sponsorship/donation received: o Cash; or o Goods; or o Services; or o A hybrid of the above. | 2014-09-18 | 2014-10-15 | A policy on sponsorship/donation need to be prepared (define what are the impact for sponsorship in cash, goods, services) |  | Yes | To prepare a new policy on sponsorship and dontation | No | N/A
| b) Establish process to determine whether PGT shall need to issue tax invoice to the sponsor / donor based on:- i. Any benefits provided by PGT to the sponsor / donor (e.g. advertising, free table during functions, etc) – to issue tax invoice to the sponsor / donor; or ii. No benefit provided by PGT (pure donation) – no issuance of tax invoice required. | 2014-09-18 | 2014-09-17 | Refer to the spreadsheet for sponsorship provide & received by PGT |  | Yes | Prepare a process/procedure to determin the tax invoice involvement | No | N/A
| c) If the issue of a tax invoice is required, establish a process to determine the value of the sponsorship / donation and the amount of GST to be accounted in the tax invoice. | 2014-09-18 |  | To determine the open market value of the sponsorship received/provided |  | Yes | To discuss with department head on the open market value | No | N/A
| d) Establish processes to ensure that GST output tax is properly captured and accounted in the GST return Form GST-03 in the correct taxable period. | 2014-09-18 |  | To prepare a process of capture output tax for sponsorship of goods, amd services |  | Yes | To discuss with PwC
| Sponsorship / Donation made by PGT a) Identify nature of sponsorship/donation given: o Cash; or o Goods; or o Services; or o A hybrid of the above. | 2014-09-18 |  | Sponsorship received by PGT : a) Sponsorship of air tickets for guests b) Cash Sponsorship for events | a & b) by mention sponsor's name and logo in media release, publicity |  |  | No | N/A
| b) Establish process to determine whether PGT shall need to issue tax invoice / received tax invoice as follows:- | 2014-09-18 |  | Refer to the spreadsheet for sponsorship provide & received by PGT |  | Yes | Prepare a process/procedure to determin the tax invoice involvement | No | N/A
| c) If the issue of tax invoice is required, establish process to determine the value of the sponsorship / donation subjected to GST and the amount of GST to be accounted in the tax invoice. | 2014-09-18 |  | To determine the open market value of the sponsorship /received provided |  | Yes | To discuss with department head on the open market value e.g Services / promotion of event in website/facebook | No | N/A
| d) If there is input tax is claimable, establish process to ensure tax invoice are received for input tax claim purposes. | 2014-09-18 | 2014-10-15 | A process for GST output tax and input tax to be prepare |  | Yes | To prepare a process/procedure of input tax for sponsorship given | No | N/A
| e) Establish processes to ensure that GST output and input tax are properly captured and accounted in the GST return Form GST-03 in the correct taxable period. | 2014-09-18 | 2014-10-15 | A process for GST output tax and input tax to be prepare |  | Yes | To prepare a process/procedure to account for output tax | No | N/A
3 | Establish process and policy to ensure that all future contracts or arrangements related to sponsorship / donation arrangement have GST clauses (inclusive / exclusive). | 2014-09-18 | 2014-10-15 | To set a policy for sponsorship provided/received |  | Yes | To set a policy to ensure all gst clauses are include in sponsorship | No | N/A
4 | Determine and implement the processes and systems changes required to incorporate the GST impact and implications related to sponsorship / donation received / made. | 2014-09-18 | 2014-10-15 | Process and system changes to be implemented when the policy & procedure is ready |  | Yes | To implement the system and process based on GST guidelines | No | N/A
5 | Review current accounting and recording of sponsorship / donation (received / made) and determine the appropriate tax codes to be applied. | 2014-09-18 |  | Refer to tax coding |  | Yes | To analyse current accounting (sponsorship provided/received) | Yes | Refer to tax coding
6 | Educate employees on the processes, policies and systems changes. | 2014-09-18 |  | To brief and educate staff when the new policies is ready |  | No | N/A

## Sponsorhip (by PGT)
Sponsorship provided by PGT :
- Publicity
- Performance
- Cash
- Goods
- Hotel/Dinner/Tour
Benefit in returns :
- Logo
- Booth/ Goods
- by mention PGT in their media release
Tax Invoice to be issued by recipient :
- based on the value of the goods received
No tax invoice involve
Entitle to claim the input tax
(Except for Hotel/Tours/Dinner)
*Block Input Tax
NO
YES

## Sponsorhip Received
Sponsorship received :
- Publicity
- Cash
- Hotel/Dinner/Tour
Benefit given :
- Putting donor's logo / name in our media release/publicity
Tax Invoice to be issue by PGT:
- based on the value of the goods received
- inclusive of GST
No tax invoice involve
NO
YES