## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 27 | Payment to Federal & State Governments, Statutory Bodies and Local Authorities |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and list all payments made to local authorities and statutory bodies. | 2014-09-18 | 2014-09-13 | Payment made to local authorities & statutory bodies : - Company Car Road Tax - License fees for Tourist Information Centre (TIC) - PTPTN loan repayment in respect of staff's salary - EPF, SOCSO, PCB in respect of staff's salary - Adsvetising permit in TIC - Deposit to MPPP for banners | No | N/A | No | N/A
2 | Review and confirm prior to GST implementation whether GST would apply on the relevant payment. | 2014-09-18 | 2014-09-13 | No GST impact on these payment (out of scope) | No | N/A | No | N/A
3 | Implement and determine the processes and system changes to track and confirm whether GST applies on a payment to local authorities and statutory bodies prior to making payment. | 2014-09-18 | 2014-09-13 | Nil - All payment to local authorities & statutory bodies are under R&E (Regulations & Enforcement) | No | N/A | No | N/A
4 | Establish a process to ensure PGT do not claim input tax on payments to federal & state governments. | 2014-09-18 | 2014-09-13 | A process/procedure of input tax credit claimable to be prepared | Yes | To check with PwC consutant on what are the payment to local statutory bodies is allow for input tax claim | No | N/A
5 | Implement processes and systems changes. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
6 | Educate staff on the processes and systems changes. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A