## GST Checklist-PGT
PENANG GLOBAL TOURISM SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: <TBC>
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A1 | GST 01 | Registration for GST | Michelle | On Going | 2014-11-21 |  | Not yet started
A | GST 05 | Approved Tourist Refund Scheme Outlet | Janice, Evelyn, Michelle |  |  |  | Not yet started
A | GST 02 | Budgeting Resources Requirement for GST Implementation | Michelle | August And September | 2014-08-29 |  | Not yet started
A | GST 04 | Preferred Vendor Management | Janice, Yani, Jason, Michelle |  | 2014-09-05 |  | In Progress
A | GST 06 | Price Rebalancing | Michelle |  |  |  | Done
B | GST 10 | Time of Supply | Janice,Michelle | September and October | 2014-09-12 |  | Not yet started
B | GST 12 | Sundy Income and Miscellaneous Expenditure | Janice, Michelle |  |  |  | Not yet started
B | GST 17 | Blocked Input Tax | Michelle |  |  |  | Not yet started
B | GST 18 | Entertainment Expenditure | Hooi Leng, Jason, Pauline, Michelle |  | 2014-09-19 |  | Not yet started
B | GST 19 | Employee Benefits | Hooi Leng, Michelle |  |  |  | Not yet started
B | GST 20 | Reimbursement of staff expenses/claims | Pauline, Jason, Michelle |  |  |  | Not yet started
B | GST 21 | Goods provided for free | Affa, Darren, Michelle, Jason |  |  |  | Not yet started
B | GST 22 | Free services | Michelle, Jason |  |  |  | Not yet started
B | GST 26 | Sponsorship | All Staffs |  |  |  | Not yet started
B | GST 27 | Payment to Federal & State Governments, Statutory Bodies and Local Authorities | Michelle |  | 2014-09-26 |  | Not yet started
B | GST 11 | Commission received | Janice, Michelle |  |  |  | Not yet started
B | GST 28 | GST/VAT Incurred overseas | Yani, Pauline, Michelle |  | 2014-10-03 |  | Not yet started
B | GST 16 | Imported Services (Reverse Charge) | Yani, Pauline, Jason, Michelle |  |  |  | Not yet started
B | GST 23 | Disposal of fixed assets | Michelle |  |  |  | Not yet started
C | GST 13 | De minimis and Incidental Financial Supplies | Michelle | October | 2014-10-10 |  | Not yet started
D | GST 07 | Tax Coding for GST | Michelle | October | 2014-10-24 |  | Not yet started
D | GST 09 | Issuance of Tax Invoices | Michelle |  |  |  | Not yet started
D | GST 15 | Accounting Recognition vs GST Recognition for Input Tax Claim | Michelle |  | 2014-10-31 |  | Not yet started
E | GST 08 | Record Keeping requirements for GST purposes | Michelle | November | 2014-11-07 |  | Not yet started
E | GST 14 | Documentation to Claim Input Tax Credit | All Staffs |  |  |  | Not yet started
E | GST 24 | GST on Lost/Destroyed/Stolen/Obsolete Stock | Janice, Affa, Evelyn, Michelle |  | 2014-11-14 |  | Not yet started
E | GST 25 | Company Cars | Michelle, Hooi Leng |  |  |  | Not yet started
F | GST 03 | CAPEX | Mr Ooi Chok Yan, Michelle | November | 2014-11-21 |  | Not yet started